## Sprint 0
Sprint 0
Goal | Get Started
Backlog
Story ID | Story | Size | New | In Progress | To be verified | Done | Impeded | Description | Assignee | Worked hours | Remaining hours
TX1 | Create user stories | 5 |  |  |  | x |  | Create initial stories |  | 3 | 0
TS2 | Create project structure | 5 |  |  |  | x |  | Add constants to LeahConsts.hrh |  | 1 | 0
TS2 | Create project structure | 5 |  |  |  | x |  | Create structure for Server |  | 2 | 0
TS2 | Create project structure | 5 |  |  |  | x |  | Create structure for ServLib |  | 1 | 0
TS2 | Create project structure | 5 |  |  |  | x |  | Create structure for CommonFramework |  | 1 | 0
TS2 | Create project structure | 5 |  |  |  | x |  | Add server classes to Server component |  | 2 | 0
Total |  |  | 0 | 0 | 0 | 6 | 0 |  |  | 10 | 0

## Sprint 1
Sprint 1
Goal | Get something working
Backlog
Story ID | Story | Size | New | In Progress | To be verified | Done | Impeded | Description | Assignee | Worked hours | Remaining hours
TS5 | Create support for properties | 8 |  |  |  | x |  | Create properties |  | 12 | 0
TS7 | Create support for events | 8 |  |  |  | x |  | Create events |  | 12 | 0
TS6 | Create support for data binding between properties | 8 |  |  |  | x |  | Create data binding |  | 12 | 0
TS8 | Create support for read only properties | 2 |  |  |  | x |  | Create read only properties |  | 2 | 0
TS4 | Create control base class | 13 |  |  |  | x |  | Take properties from .NET Windows Forms |  | 4 | 0
TS4 | Create control base class | 13 |  |  |  | x |  | Take events from .NET Winfows Forms |  | 8 | 0
TS4 | Create control base class | 13 |  |  |  | x |  | Implement infrastructure for Control |  | 8 | 0
Total |  |  | 0 | 0 | 0 | 7 | 0 |  |  | 58 | 0

## Sprint 2
Sprint 2
Goal | Do the infrastructure
Backlog
Story ID | Story | Size | New | In Progress | To be verified | Done | Impeded | Description | Assignee | Worked hours | Remaining hours
TS3 | Create UI framework | 40 |  |  |  | x |  | Implement UI framework | MC | 50 | 0
TS1 | Create support for XML loading | 13 |  |  |  | x |  | Implement XML tools | MC | 50 | ?
Total |  | 53 | 0 | 0 | 0 | 2 | 0 |  |  | 100 | 0

## Sprint 3
Sprint 3
Goal | See the first actual results
Backlog
Story ID | Story | Size | New | In Progress | To be verified | Done | Impeded | Description | Assignee | Worked hours | Remaining hours
US17 | As a User I want to see a start screen out of the box | 8 |  |  |  | x |  | Create OoB intro view class | MC | 1 | 0
US17 | As a User I want to see a start screen out of the box | 8 |  |  |  | x |  | Create welcome label | MC | 1 | 0
US17 | As a User I want to see a start screen out of the box | 8 |  |  |  | x |  | Create title label | MC | 1 | 0
US17 | As a User I want to see a start screen out of the box | 8 |  |  |  | x |  | Create intro text label | MC | 1 | 0
US17 | As a User I want to see a start screen out of the box | 8 |  |  |  | x |  | Create button basic class | MC | 1 | 0
Us17 | As a User I want to see a start screen out of the box | 8 |  |  |  | x |  | Add button properties and events | MC | 2 | 0
US17 | As a User I want to see a start screen out of the box | 8 |  |  |  | x |  | Implement touch triggering of click | MC | 2 | 0
US17 | As a User I want to see a start screen out of the box | 8 |  |  |  | x |  | Add begin button to intro view | MC | 1 | 0
US17 | As a User I want to see a start screen out of the box | 8 |  |  |  | x |  | Reimplement padding as TRect with external properties | MC | 1 | 0
Total |  | 72 | 0 | 0 | 0 | 9 | 0 |  |  | 11 | 0

## Sprint 4
Sprint 4
Goal | Load the UI from XML
Start Date
End Date | 2012-01-20
Backlog
Story ID | Story | Size | New | In Progress | To be verified | Done | Impeded | Description | Assignee | Worked hours | Remaining hours
TS10 | Implement layout support | 13 |  |  |  | x |  | Implement canvas | MC | 2 | 0
TS10 | Implement layout support | 13 |  |  |  | x |  | Implement attached properties in perl script | MC | 1 | 0
TS10 | Implement layout support | 13 |  |  |  | x |  | Implement parent suport in perl script | MC | 1 | 0
TS10 | Implement layout support | 13 |  |  |  | x |  | Implement Measure and Arrange in Grid | MC | 7 | 0
TS10 | Implement layout support | 13 |  |  |  | x |  | Implement only one Layout cycle | MC | 5 | 0
TS10 | Implement layout support | 13 |  |  |  | x |  | Add Grid alignment attached properties | MC | 2 | 0
TS10 | Implement layout support | 13 |  |  |  | x |  | Implement Row and Column definition in Grid | MC | 3 | 0
TS10 | Implement layout support | 13 |  |  |  | x |  | Implement stack panel | MC | 5 | 0
TS9 | Create support for enumeration values | 3 |  |  |  | x |  | Implement support for enums | MC | 2 | 0
TS9 | Create support for enumeration values | 3 |  |  |  | x |  | Implement bool parsing | MC | 1 | 0
TS9 | Create support for enumeration values | 3 |  |  |  | x |  | Implement separate enums | MC | 1 | 0
Total |  |  | 0 | 0 | 0 | 11 | 0 |  |  | 30 | 0

## Sprint 5
Sprint 5
Goal | Have the config application
Start Date | 2012-01-20
End Date | 2012-01-27
Backlog
Story ID | Story | Size | New | In Progress | To be verified | Done | Impeded | Description | Assignee | Worked hours | Remaining hours
TS11 | Implement forms management | 3 |  |  |  | x |  | Implement Form unload | MC | 1 | 0
TS11 | Implement forms management | 3 |  |  |  | x |  | Implement form loading and unloading when switching between forms | MC | 1 | 0
TS11 | Implement forms management | 3 |  |  |  | x |  | Check all ASSERTs to run dispensable code. | MC | 1 | 0
TS11 | Implement forms management | 3 |  |  |  | x |  | Optimize form layout | MC | 0 | 0
TS11 | Implement forms management | 3 |  |  |  | x |  | Optimize attached properties default values | MC | 1 | 0
US19 | As a User I can see the Config application in the applications list on the phone | 13 |  |  |  | x |  | Study the Application Framework in Symbian sources | MC | 3 | 0
US19 | As a User I can see the Config application in the applications list on the phone | 13 |  |  |  | x |  | Implement necessary code to display the application in the apps list | MC | 10 | 0
US19 | As a User I can see the Config application in the applications list on the phone | 13 |  |  |  | x |  | Close application via App List exit | MC | 1 | 0
TS13 | Implement images manager | 8 |  |  |  | x |  | Implement Images Manager singleton | MC | 1 | 0
TS13 | Implement images manager | 8 |  |  |  | x |  | Implement image identification by number | MC | 1 | 0
TS13 | Implement images manager | 8 |  |  |  | x |  | Implement image loading and unloading | MC | 1 | 0
TS13 | Implement images manager | 8 |  |  |  | x |  | Implement reference counting for images | MC | 3 | 0
Total |  | 86 | 0 | 0 | 0 | 12 | 0 |  |  | 24 | 0

## Sprint 6
Sprint 6
Goal | Make it useful
Start Date | 2012-01-30
End Date | 2012-02-03
Backlog
Story ID | Story | Size | New | In Progress | To be verified | Done | Impeded | Description | Assignee | Worked hours | Remaining hours
US21 | As a User I can have the application in both portrait and landscape | 5 |  |  |  | x |  | Check what messages are sent when switching orientation | MC | 1 | 0
US21 | As a User I can have the application in both portrait and landscape | 5 |  |  |  | x |  | Handle the orientation the message and re-layout the app | MC | 3 | 0
US20 | As a User I can type in usernames and passwords | 13 |  |  |  | x |  | Study how to create a FEP aware editor | MC | 3 | 0
US20 | As a User I can type in usernames and passwords | 13 |  |  |  | x |  | Implement custom keyboard base | MC | 3 | 0
US20 | As a User I can type in usernames and passwords | 13 |  |  |  | x |  | Implement keyboard multipage support | MC | 2 | 0
US20 | As a User I can type in usernames and passwords | 13 |  |  |  | x |  | Implement pressed key popup | MC | 6 | 0
US20 | As a User I can type in usernames and passwords | 13 |  | x |  |  |  | Implement keyboard singleton | MC | 0 | 3
US20 | As a User I can type in usernames and passwords | 13 |  |  |  | x |  | Implement numbers page | MC | 1 | 0
US20 | As a User I can type in usernames and passwords | 13 |  |  |  | x |  | Implement symbols page | MC | 1 | 0
US20 | As a User I can type in usernames and passwords | 13 | x |  |  |  |  | Integrate keyboard at application level | MC | 0 | 2
US20 | As a User I can type in usernames and passwords | 13 | x |  |  |  |  | Implement form scrolling when keyboard pops up | MC | 0 | 2
US20 | As a User I can type in usernames and passwords | 13 | x |  |  |  |  | Implement keyboard popup on demand | MC | 0 | 2
US20 | As a User I can type in usernames and passwords | 13 |  |  |  | x |  | Change Paint and other event args members from properties to simple members | MC | 0 | 2
US20 | As a User I can type in usernames and passwords | 13 | x |  |  |  |  | Add WindowLocation property to forms | MC | 0 | 3
Total |  | 166 | 4 | 1 | 0 | 9 | 0 |  |  | 20 | 14

## Product Backlog
Backlog item types |  |  |  | Usual hours per day
Defect | Bugs, anything that doesn't work as expected |  |  | Workdays | 4
Spike | Study |  |  | Weekend | 4
Tax | Process overhead
Tech Story | Story proposed by the team
User Story | Story that has immediate value to the user
Backlog item status
Not Started | Not worked on yet
In Progress | Currently working on the item
Done | Implemented, tested, potentially shippable
Impeded | Item cannot be implemented due to impediments
N/A | Not applicable, status unknown. Hopefully this is temporary
Product Backlog
ID | Type | Description | Size | Status | Sprint | Worked Hours | Remaining hours | Hours / SP | Hours per day | Worked Days | Remaining Days
TX1 | Tax | Create user stories | 5 | Done | Sprint 0 | 3 | 0 | 0.6 | 2 | 1.5 | 0
TS2 | Tech Story | Create project structure | 5 | Done | Sprint 0 | 7 | 0 | 1.4 | 4 | 1.75 | 0
TS4 | Tech Story | Create control base class | 13 | Done | Sprint 1 | 20 | 0 | 1.5385 | 4 | 5 | 0
TS5 | Tech Story | Create support for properties | 8 | Done | Sprint 1 | 12 | 0 | 1.5 | 4 | 3 | 0
TS6 | Tech Story | Create support for data binding between properties | 8 | Done | Sprint 1 | 12 | 0 | 1.5 | 4 | 3 | 0
TS7 | Tech Story | Create support for events | 8 | Done | Sprint 1 | 12 | 0 | 1.5 | 4 | 3 | 0
TS8 | Tech Story | Create support for read only properties | 2 | Done | Sprint 1 | 2 | 0 | 1 | 4 | 0.5 | 0
TS3 | Tech Story | Create UI framework | 40 | Done | Sprint 2 | 50 | 0 | 1.25 | 4 | 12.5 | 0
TS1 | Tech Story | Create support for XML loading | 13 | Done | Sprint 2 | 50 | 0 | 3.8462 | 4 | 12.5 | 0
US17 | User Story | As a User I want to see a start screen out of the box | 8 | Done | Sprint 3 | 11 | 0 | 1.375 | 4 | 2.75 | 0
TS10 | Tech Story | Implement layout support | 13 | Done | Sprint 4 | 26 | 0 | 2 | 4 | 6.5 | 0
TS9 | Tech Story | Create support for enumeration values | 3 | Done | Sprint 4 | 4 | 0 | 1.3333 | 4 | 1 | 0
US19 | User Story | As a User I can see the Config application in the applications list on the phone | 13 | Done | Sprint 5 | 14 | 0 | 1.0769 | 4 | 3.5 | 0
TS11 | Tech Story | Implement forms management | 3 | Done | Sprint 5 | 4 | 0 | 1.3333 | 4 | 1 | 0
TS13 | Tech Story | Implement images manager | 8 | Done | Sprint 5 | 6 | 0 | 0.75 | 4 | 1.5 | 0
US21 | User Story | As a User I can have the application in both portrait and landscape | 5 | Done | Sprint 6 | 4 | 0 | 0.8 | 4 | 1 | 0
US20 | User Story | As a User I can type in usernames and passwords | 13 | In Progress | Sprint 6 | 16 | 14 | 2.3077 | 4 | 4 | 3.5
TS14 | Tech Story | Implement styles | 8 | N/A | Sprint 7 |  |  |  | 4
TS15 | Tech Story | Implement animations | 13 | N/A | Sprint 7 |  |  |  | 4
US18 | User Story | As a User I want to see a starting screen after the application is configured |  | N/A |  |  |  |  | 4
US1 | User Story | As a User I can see phone added contact is pushed to Google Contacts To be able to sync it further | 13 | N/A |  |  |  |  | 4
US2 | User Story | As a User I can see Google Contacts added contact is pushed to my phone To be able to communicate with the new contact |  | N/A |  |  |  |  | 4
US3 | User Story | As a User I can configure how often the from Google Contacts happens To control my network traffic and costs |  | N/A |  |  |  |  | 4
US4 | User Story | As a User I can configure my Google account, by selecting Username/Password To access my account |  | N/A |  |  |  |  | 4
US5 | User Story | As a User I want my Google account data to be secured To be safe if I lose my device |  | N/A |  |  |  |  | 4
US6 | User Story | As a User I can see a removed contact from Google Contacts is removed also from my phone To avoid keeping dirt on my phone |  | N/A |  |  |  |  | 4
US7 | User Story | As a User I can see a removed contact from my phone is removed also from Google Contacts To be able to remove it further from other devices |  | N/A |  |  |  |  | 4
US8 | User Story | As a User I can see a modified contact from Google Contacts modified also on my Phone To avoid data consistency issues |  | N/A |  |  |  |  | 4
US9 | User Story | As a User I can see a modified contact from my phone modified also on Google Contacts To avoid data consistency with other devices |  | N/A |  |  |  |  | 4
US10 | User Story | As a User I can see the synchronizing status To be able to control it. |  | N/A |  |  |  |  | 4
US11 | User Story | As a User I can stop a synchronization from running To avoid traffic if I need to make changes |  | N/A |  |  |  |  | 4
US12 | User Story | As a User I can see a notification when the sync is running To have control over it |  | N/A |  |  |  |  | 4
US13 | User Story | As a User I can initiate a manual sync To sync the contacts when I want to |  | N/A |  |  |  |  | 4
US14 | User Story | As a User I can sync all my contacts when out-of-the-box To have a nice experience |  | N/A |  |  |  |  | 4
US15 | User Story | As a User I can configure when the sync happens To control my traffic and costs |  | N/A |  |  |  |  | 4
US16 | User Story | As a User I can configure the sync not to happen when roaming To control my costs |  | N/A |  |  |  |  | 4
US22 | User Story | As a User I can install the application on the phone with or without dependencies | 5 | N/A |  |  |  |  | 4
Total |  |  | 207 |  | 0 | 253 | 14 | 1.4771 | 3.9459 | 64 | 3.5

## User Stories
User Stories
Impediments list
Story ID | Story | Acceptance Criteria
US17 | As a User I want to see a start screen out of the box | Welcome text top left
US17 | As a User I want to see a start screen out of the box | Title top left, under the welcome text
US17 | As a User I want to see a start screen out of the box | Application intro text under the title
US17 | As a User I want to see a start screen out of the box | Begin button in bottom right
TS9 | Create support for enumeration values | Something like a table with symbol and numeric value. The parser would look for the symbol and read the associated value.
Total

## Release Plan
Release Plan
Sum of Size | Column Labels
Row Labels | Tax | Tech Story | User Story | Grand Total
(blank) |  |  | 13 | 13
As a User I can see phone added contact is pushed to Google Contacts To be able to sync it further |  |  | 13 | 13
As a User I can see Google Contacts added contact is pushed to my phone To be able to communicate with the new contact
As a User I can configure how often the from Google Contacts happens To control my network traffic and costs
As a User I can configure my Google account, by selecting Username/Password To access my account
As a User I want my Google account data to be secured To be safe if I lose my device
As a User I can see a removed contact from Google Contacts is removed also from my phone To avoid keeping dirt on my phone
As a User I can see a removed contact from my phone is removed also from Google Contacts To be able to remove it further from other devices
As a User I can see a modified contact from Google Contacts modified also on my Phone To avoid data consistency issues
As a User I can see a modified contact from my phone modified also on Google Contacts To avoid data consistency with other devices
As a User I can see the synchronizing status To be able to control it.
As a User I can stop a synchronization from running To avoid traffic if I need to make changes
As a User I can see a notification when the sync is running To have control over it
As a User I can initiate a manual sync To sync the contacts when I want to
As a User I can sync all my contacts when out-of-the-box To have a nice experience
As a User I can configure when the sync happens To control my traffic and costs
As a User I can configure the sync not to happen when roaming To control my costs
As a User I want to see a starting screen after the application is configured
Sprint 0 | 5 | 5 |  | 10
Create user stories | 5 |  |  | 5
Create project structure |  | 5 |  | 5
Sprint 1 |  | 39 |  | 39
Create control base class |  | 13 |  | 13
Create support for properties |  | 8 |  | 8
Create support for data binding between properties |  | 8 |  | 8
Create support for events |  | 8 |  | 8
Create support for read only properties |  | 2 |  | 2
Sprint 2 |  | 53 |  | 53
Create UI framework |  | 40 |  | 40
Create support for XML loading |  | 13 |  | 13
Sprint 3 |  |  | 8 | 8
As a User I want to see a start screen out of the box |  |  | 8 | 8
Sprint 4 |  | 16 |  | 16
Implement layout support |  | 13 |  | 13
Create support for enumeration values |  | 3 |  | 3
Sprint 5 |  | 11 | 13 | 24
As a User I can see the Config application in the applications list on the phone |  |  | 13 | 13
Implement forms management |  | 3 |  | 3
Implement images manager |  | 8 |  | 8
Sprint 6 |  |  | 18 | 18
As a User I can have the application in both portrait and landscape |  |  | 5 | 5
As a User I can type in usernames and passwords |  |  | 13 | 13
Grand Total | 5 | 124 | 52 | 181

## Impediments
Impediments status
Not solved | Impediments that are not solved
In Progress | Impediment that is currently being solved or analyzed
Solved | Impediment solved
Impediments
Impediments list
Story ID | Story | Status | Description | Assignee
TS1 | Create support for XML loading | Solved | Use the compiler debug information to get the variables types. Use those types to perform different kind of assignments, depending on type. For example, do not use quotes for numbers. | MC
US17 | As a User I want to see a start screen out of the box | Solved | Properties assignment does not work properly. KERN-EXEC 3 when assigning directly 2 properties. Paddings cannot be set with "=" operator | MC
Total |  | 2

## Sprint Template
Sprint #
Goal | Sprint Goal
Start Date
End Date
Backlog
Story ID | Story | Size | New | In Progress | To be verified | Done | Impeded | Description | Assignee | Worked hours | Remaining hours
| #N/A | #N/A
Total |  | #N/A | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0